## Summary
GROUP: | SKNCOE2
project: | Data Generator
# | Task | start DT | end DT | actual start DT | actual end DT
1 | POC | 2011-10-10 | 2011-10-14
2 | Design
3 | Class Diagrams
4 | Class implementation
5 | implementation data generator
6 | implementation data Loader
7 | documentation

## Tasks
# | Type | Tasks_id | details | assigned to | time(days) | expected ST | expected ET | actual completion time | Reason, if delayed
1 | POC | [8 empty] | Bela
|  | 1.1 | deciding on data structures to store the XML | Ritesh | 1 | 2011-10-10 | 2011-10-11 |  |  | Ritesh
|  | 1.2 | Parsing of XML and storing in the data structure | Ritesh | 0.5 | 2011-10-11 | 2011-10-11 12:00 |  |  | sakshi
|  | 1.3 | writing data generation stubs | Bela | 1 | 2011-10-10 | 2011-10-11 |  |  | abhishek
|  | 1.4 | integration and geneating flat file o/p(csv) | Ritesh | 1 | 2011-10-11 12:00 | 2011-10-12 12:00 |  |  | nandlal
|  | 1.5 | unit testing with multiple scenarios | sakshi | 1 | 2011-10-12 12:00 | 2011-10-13 12:00 |  |  | All
|  | 1.6 | write data loaded application(postgres): a standalone odbc program to load the csv | sakshi | 1 | 2011-10-13 12:00 | 2011-10-14 12:00
|  | 1.7 | write sample programs for boost library using multi threaded library | Ritesh | 1 | 2011-10-12 12:00 | 2011-10-13 12:00
|  | 1.8 | write sample programs for using STL using following: iterators,functors, algorithms of sorting and searching, adaptors | Bela | 2 | 2011-10-11 | 2011-10-13
|  | 1.9 | review meeting | All |  | 2011-10-14 | 2011-10-14
2 | Design- FS
|  | 2.1 |  |  |  | 2011-10-15 | 2011-11-04
2.2
2.3
3 | Class Diagrams
|  | 3.1 |  |  |  | 2011-11-05 | 2011-11-18
3.2
3.3
4 | Class implementation
|  | 4.1 |  |  |  | 2011-11-19 | 2011-12-02
4.2
4.3
5 | implementation data generator |  |  |  |  | 2011-12-03 | 2011-12-24
5.1
5.2
5.3
5.4
5.5
6 | implementation data Loader |  |  |  |  | 2011-12-03 | 2011-12-24
6.1
6.2
6.3
6.4
7 | documentation |  |  |  |  | 2011-01-02 | 2011-01-12
7.1
7.2
7.3
7.4
7.5
7.6
Formulas:
expected ET = [expected ST]+[time(days)]
expected ST = [expected ET, row above]